## Sheet1
# | Item | Priority | Comments
1 | Accommodate for option type and strike price along with symbol in option price capture component | 10 | DONE
2 | Change all price values to float(10,2) in DB | 4 | To be done later as round_price_value function also checks for negative prices
3 | Check why IS_DUMMY_OPTION_DATA_REQUIRED not working | 10 | DONE
4 | Other optimisations to DB components | 4 | 1. Remove Unwanted variables 2. record time taken for major steps 3. optimise 'Check price trend' cycle 4. Avoid Symbol,Option Type, Strike Price Option wherever possible 5. Other improvements like point 4 above
5 | Deploy application on cloud | 1 | target instance type combination - 1. 2 to 3 t1.micro instances 2. 1 t1 micro and 1 t1. medium or t1.small as required. - THERE IS NO PROBLEM WITH THE COST | Problem with Data Capture. Process Closes on remote VM once you putty terminal is closed/inactive.
6 | Check if ECS can be enabled | 4 | ECS not required as of now
7 | Study Zerodha API | 10 | Done
8 | Integrate with Zerodha API | 10 | Done
9 | Test with appropriate confidence values for 19th | 10 | DONE
10 | Design for multiple accounts | 2 |  | No Application Design. Multiple accounts will have separate deployments. Maybe Daystart activities need to be centralised.
11 | How to handle half filled orders | 2 | Testing Pending in live environment | Test with Dummy Data.
12 | UI to fill EOD data Output to basis_for_calls and selected_instrument table | 10 | Excel Import to be done | Check with Parveen if UI required
13 | Final Process Work Flow Development | 10 | Cancel Flow remaining | Done
13 | DIG OUT PARAMETERS FROM CALCULATIONS | 3 | Done for now
14 | WRITE LOGIC FOR CLOSING UNCLOSED ORDERS AT 3.25 P.M | 4 | MAKE ORDER SELL PRICE AT 0.SELL IN MARKET | TBD with Parveen
15 | WRITE LOGIC TO SELL MARKET ORDERS AT BID PRICE | 10 | CHECK ZERODHA API IF THEY PROVIDE BID PRICES. THEN TRY TO SELL ONLY IF MINIMUM LOSS BID IS AVAILABLE | Done | TBD with Parveen
16 | WRITE LOGIC FOR CLOSING UNCLOSED BUY ORDERS AT 2.45 | 10 | WRITE LOGIC TO CANCEL ORDERS AT 2.45 | Done
17 | Get Webview Working | 2
18 | add Expiry date to instruments | 10 |  | Done
19 | Change buy and sell order factor - calculate factor from dummy option price calculation | 10 | done
20 | MONITOR - Check if option prices data saving pauses - aim for single websocket and worker threads to extract data | 4 | Patch written - Testing Pending. Multithreading remaining | Testing Done. Multithreading MAYBE not required
21 | Capture High Price in option price data | 10 | Done. Testing Pending | Testing Done.
22 | Limit Buy order price to 75 % of high price | 4 | Limited to 92.5 % | Willl try lesser value depending upon results.
23 | Once Data model is finalised, check where columns need to be made not null ( previously ignored because no data was available when column was added) | 3
24 | Scrip based margin | 3 |  | To be done in input File
25 | After trade calculate and apply cumulative strength | 2 |  | To be Decided.
26 | Better management of trailing stop loss | 2
27 | strength threshold factor for negative trend.. Say 80% | 1 | Done | Play with different values.
28 | SET CLOUD ALERT WHEN MAIN STORED PROCEDURE GIVES ERROR | 2

## FLOWS TO BE TESTED
# | Item | Priority | Comments
1 | CALCULATE_EFFICIENT_BUY_ORDER_PRICE | 4
2 | CALCULATE_EFFICIENT_SELL_ORDER_PRICE | 4
3 | CALCULATE_QUANTITY_FROM_MARGIN | 2
4 | CHECK_SLOW_SL_ORDER_POSITION | 1
5 | CHECK_SLOW_SL_ORDER_POSITION_FOR_OFFER_PRICE | 1
6 | FAST_STOP_LOSS_TRIGGER | 1
7 | PUT_MODIFY_OPTION_SELL_ORDER_EVENT | 2
8 | RETRY_PUT_MODIFY_OPTION_BUY_ORDER_EVENT | 3
9 | RETRY_PUT_MODIFY_OPTION_SELL_ORDER_EVENT | 3
10 | UPDATE_SL_PRICE | 1
11 | VALIDATE_SELL_ORDER_IF_MARKET_ORDER_HIT | 1